## Knowledge Sharing Workshop Work
Knowledge Sharing Workshop Work Plan
Muslim Women’s Family Law Legal Rights
Canadian Council of Muslim Women
At least one co-facilitator should have a legal background in Canadian family law*
CCMW chapter workshop facilitator (choose from drop-down list):
Full name of CCMW chapter workshop leader(s):
Email address(es):
Phone number(s):
Profession:
| Legal background in Canadian family law? (Check the box if yes) | FALSE
Full Name of Individual/Organizational Co-facilitator(s):
Email address(es):
Phone number(s):
Individual profession or organizational focus:
| Legal background in Canadian family law? (Check the box if yes) | FALSE
| Task description | Start date | Finish date | Status
start
| PLANNING |  |  | Incomplete
| Assign Workshop roles: Facilitators, Facility set-up, Facility clean-up, Marketing, etc. |  |  | Incomplete
1 | Setup phone meeting with Project Coordinator (Sabrine Azraq) |  |  | Incomplete
1.1 | Send introduction email to individual/organizational co-facilitators stating interest in running workshop |  |  | Incomplete
1.2 | Confirm date and location of workshop with co-facilitators |  |  | Incomplete
1.3 | Develop agenda for workshop |  |  | Incomplete
1.4 | Develop welcome and overview slides for presentation |  |  | Incomplete
1.5 | Draft list of required supplies for workshop |  |  | Incomplete
1.6 | Send background material, sample agenda and project plan to interested volunteers by email and ask them to sign up for specific tasks |  |  | Incomplete
1.7 | Email brief (design and content) of workshop graphic to the Graphic Designer |  |  | Incomplete
1.8 | Develop list of community partners to advertise through |  |  | Incomplete
1.9 | Purchase required supplies for workshop |  |  | Incomplete
1.10 | Brainstorm catering options |  |  | Incomplete
1.11 | Get quotes for catering options |  |  | Incomplete
1.12 | Contact preferred caterer to purchase and arrange pick-up |  |  | Incomplete
1.13 | Pre-workshop meeting with facilitators and volunteers to discuss outstanding questions and review plan for the day-of |  |  | Incomplete
2 | OUTREACH |  |  | Incomplete
2.1 | Setup phone meeting with Project Coordinator |  |  | Incomplete
2.2 | Send workshop graphic to co-facilitators to distribute |  |  | Incomplete
2.3 | Send workshop graphic to Project Coordinator to add to CCMW website, social media, newsletter) |  |  | Incomplete
2.4 | Send workshop graphic to community groups to distribute |  |  | Incomplete
3 | IMPLEMENTATION |  |  | Incomplete
3.1 | Setup phone meeting with Project Coordinator |  |  | Incomplete
3.2 | Track and manage workshop reservations |  |  | Incomplete
3.3 | Create signup sheet with the following columns: Last name, First name, Organization Name, Position Title, Signature |  |  | Incomplete
3.4 | Set-up (registration table, room layout, food) |  |  | Incomplete
3.5 | Conduct workshop (including distribution of evaluations) |  |  | Incomplete
4 | CLOSE-OUT |  |  | Incomplete
4.1 | Setup phone meeting with Project Coordinator |  |  | Incomplete
4.2 | Send thank you emails to co-facilitators, participants, representatives from community groups, volunteers |  |  | Incomplete
4.3 | Email Project Coordinator completed expense form |  |  | Incomplete
4.4 | Email Project Coordinator sign-up sheet |  |  | Incomplete
4.5 | Email Project Coordinator scanned evaluations |  |  | Incomplete
Email Project Coordinator report on results of Workshop